## Migration_Checklist
S.No | Action Item | Comment(Yes/No/NA)
1 | Copy all logins with Permission
2 | Compare SP_CONFIGURE options between current and new server(CPUs, Memory, MAXDOP,Cost threshold, etc.,)
3 | Copy Server level Triggers if any.
4 | Run DBCC CHECKDB on all databases in new server
5 | Run update stats on all databases in new server
6 | Check all required maintence Jobs created(Backup, DBCC, Index maintenance, etc.,) in new server
7 | Check serivce accounts between current and new servers for SQL Server, SQL Server Agent, SSIS, SSRS.
8 | Copy all SQL Server agent Jobs
9 | Copy all SQL Server alerts
10 | Copy all SQL Server operators
11 | Copy all Linked servers, Password required while scriptout.
12 | Copy if any user defined server level role
13 | Copy DB Mail Profile and its settings
14 | Copy if any Proxy accounts and credentials
15 | Check disk space for restore and copy backup files in new server.
16 | Script out replication if any replication configured
17 | Check if any certificates and TDE configured. Configure accordingly in server(Master Key creation, copy certiifcates, etc.,)
18 | Compare Database propeties between current and new server after restore on new server(recovery model, Compatibility, DB Owner, etc.,)
19 | Check if any Database enabled with CDC and use Keep_CDC option while restore on new server
20 | Check if any SSIS pacakges need to be migrate
21 | Check if any SSRS reports need to be migrate
22 | While migrating SSRS reports, make sure take backup of encryption key from current server and restore it on new server
23 | Check SSRS configuration use RSWindowsNegotiate, instead of RSWindowsNTLM in SSRS config file
24 | Check if CLR_ENABLED ON for any of the database, make sure enable in new server
25 | Check if TRUSTWORTHY ON for any of the database, make sure enable in new server
26 | After cutover of SSRS-old to SSRS-new & changing server names, make sure point SSRS database back to SSRS-old
27 | Make sure if Task Scheduler jobs exist, we migrate them also (or ask customer based on Windows support)
28 | Needed to disable Task Scheduler checks if machines that hosts SentryOne is lower version OS than target. Otherwise it will generate XML data error